## Slide 1
2020 IMPLEMENTATION:
Region | CoE | Courses planned | Delivery mode | Original dates | Final dates | Status | Number of participants registered | Number of participants certified | End-of training reports
AFR | AFRALTI | Digital Broadcasting Content Regulation in a Converged Environment | online | 14-Feb | 3-28AUG20 | implemented | 4 | 4 | received
AFR | AFRALTI | Radio Frequency Spectrum Economy and Market Valuation Based on Digital Dividend (removed mid-June SC meeting) | face-to-face | 13-Mar |  | cancelled | NA | NA | NA
AFR | AFRALTI | Digital Broadcasting Masterclass | online | 4-8MAY20 | 30NOV-24DEC20 | cancelled | NA | NA | NA
AFR | AFRALTI | Spectrum Management Masterclass (removed mid-June SC meeting) | online | 06-17JUL20 |  | cancelled | NA | NA | NA
AFR | AFRALTI | Radio Frequency Spectrum Economy and Market Valuation | online | 07-18SEP20 | 7SEP-2OCT20 | implemented | 2 |  | received
AFR | AFRALTI | Digital Broadcasting Regulation in a Converged Environment | online | 02-13NOV20 | 2-27NOV20 | cancelled | NA | NA | NA
AFR | AFRALTI | Broadcast Spectrum Management | online |  | 5-30OCT20 | cancelled | NA | NA | NA
AFR | AFRALTI | Digital Broadcasting Content Regulation in a Converged Environment (removed mid-June SC meeting) | online | 05OCT20 -30OCT20 |  | cancelled | NA | NA | NA
AFR | AFRALTI | Radio Frequency Spectrum Economy and Market Valuation (2nd intake) | online | 16NOV-11DEC20 |  | ongoing | 9 |  | 
AFR | DBI | ICT Applications, Products & Services using Microsoft Office | face-to-face | 22-26JUN20 |  | cancelled | NA | NA | NA
AFR | DBI | Social Media Management and Digital Marketing | face-to-face | 10-14AUG20 |  | cancelled | NA | NA | NA
AFR | DBI | Developing Web-based Applications | face-to-face | 21-25SEP20 |  | cancelled | NA | NA | NA
AFR | DBI | Information and Cybersecurity Principles and Practices | online | 05-30OCT20 |  | cancelled | NA | NA | NA
AFR | DBI | Child Online Protection: Consumer Awareness on Cybercrimes | face-to-face | 20-21OCT20 |  | cancelled | NA | NA | NA
AFR | DBI | Digital Evidence and Cyber Forensics for Judicial Officers, Investigators, Legal Practitioners & Prosecutors | face-to-face | 02-06NOV20 |  | cancelled | NA | NA | NA
AFR | DBI | Emerging Cybercrime Trends: Cybercrime Investigations and Mobile Forensics for Security Intelligence, Investigators and Law Enforcement Officers | face-to-face | 09-13NOV20 |  | cancelled | NA | NA | NA
40 Trainings Planned / 13 Trainings Implemented
615 Registered / 76 Certified
(as of 1 December 2020)

## Slide 2
CoE | Courses planned | Delivery mode | Original dates | Final dates | Status | Number of participants registered | Number of participants certified | End-of training reports
ESATIC | Management de la sécurité des systèmes d'information (norme ISO/IEC 27001: lead Implémenter | face-to-face | 24-28FEB20 |  | implemented | 14 | 14 | received
ESATIC | Conception des réseaux d'accès optiques | online | 23-24MAR20 | 16NOV-12DEC20 | cancelled | NA | NA | NA
ESATIC | Comprendre l'Internet des Objets (IoT) | online | 20-24APR20 | 5-31OCT20 | cancelled | NA | NA | NA
ESATIC | Sécurité des applications d'internet et de mobile banking | online | 25-29MAY20 | 2-28NOV20 | cancelled | NA | NA | NA
ESATIC | Evolution vers la 5G: principes techniques et nouvelles opportunités économiques | online | 22-26JUN20 | 28SEP-24OCT20 | cancelled | NA | NA | NA
ESATIC | Les systèmes embarqués pour l'IoT | online | 20-24JUL20 | 23NOV-19DEC20 | cancelled | NA | NA | NA
ESATIC | Protection des données à caractère personnel | online | 01-28SEP20 | 16-28 NOV20 | implemented | 4 |  | 
ESMT | Montage et configuration d’équipements TNT | face-to-face | 9-13MAR20 |  | cancelled | NA | NA | NA
ESMT | Télévision Numérique Terrestre (TNT) et Informatique de l'audiovisuel: production, transport et diffusion | online | 13-17APR20 | 27JUL-29AUG20 | implemented | 21 | 19 | received
ESMT | Management de projet: approches préditives et agiles |  | 20APR-22MAY20 |  | cancelled | NA | NA | NA
ESMT | Régulation des services financiers digitaux et des FinTechs |  | 15-19JUN20 | 30NOV-26DEC20 | implemented | 5 |  | 
ESMT | Gestion avancée du spectre pour la 5G | face-to-face | 13-17JUL20 |  | cancelled | NA | NA | NA
ESMT | Applications et modèles économiques de la Blockchain | face-to-face | 26-30OCT20 | 28-31DEC20 | upcoming |  |  | 
ESMT | Nouveaux enjeux en gestion et contrôle du spectre | online | 30NOV-18DEC20 | 30NOV-26DEC20 | ongoing | 14 |  | 
NCB | Cybersecurity Risk Management | online | 30-31MAR20 | 28-30SEP20 | implemented | 162 | 16 | received
NCB | Cybersecurity Policy and Strategy | online | Quarter 3 2020 | 25-27NOV20 | implemented | 346 |  | 
SUP'PTIC | Quelle régulation pour l'économie numérique? | face-to-face | 10-13MAR20 |  | implemented | 12 | 12 | received
SUP'PTIC | Systèmes de paiement mobile - Transactions électroniques et monétique | face-to-face | 07-09APR20 | 18-20NOV20 | cancelled | NA | NA | NA
SUP'PTIC | Enjeux techniques et juridiques de la large bande fixe et mobile | online | 22-25APR20 | 10NOV-10DEC20 | ongoing | 5 |  | 
SUP'PTIC | Qualité d'un système large bande sans fil | online | 22-26JUN20 | 12-31AUG20 | implemented | 11 | 11 | received
SUP'PTIC | Aspects techniques et juridiques de la création d'entreprises innovantes - Services innovants : Réglementation et Régulation à l’épreuve du numérique | online | 08-11SEP20 | December | cancelled | NA | NA | NA
SUP'PTIC | Gouvernance et sécurité de l'Internet | face-to-face | 27-30OCT20 | 24-27NOV20 | cancelled | NA | NA | NA
SUP'PTIC | Stratégie numérique et transformation digitale | online | 27-29MAY20 | 30OCT-30NOV20 | implemented | 11 |  | 
SUP'PTIC | Blockchain et applications | face-to-face | 21-24JUL20 |  | cancelled | NA | NA | NA
40 Trainings Planned / 14 Trainings Implemented (+ongoing) /1upcoming
615 Registered / 76 Certified
(as of 1 December 2020)
2020 MPLEMENTATION:

## Slide 3: Overview of status of 2020 implementation in the Africa region
2020 Implementation status
40 Trainings Planned/13 Trainings Implemented – 32.5%
27 Trainings retained during June SC due to COVID-19 ≈ 37% implementation
615 Registered / 76 Certified – 12.5% due to increase in online courses
2019 Implementation status
34 Trainings Planned / 17 Trainings Implemented – 50%
273 Registered / 238 Certified – 87%
Face-to-face courses vs blended online courses
High number of participants get certified for face-to-face courses
High number and diverse registered participants but less number certified participants

## Slide 4: Overview of status of implementation in the Africa region
AFRALTI = 9 Courses/3 implemented
DBI = 7 courses/all not implemented
ESATIC = 7 Courses/2 implemented
ESMT = 7 courses/ 4 implemented
SUP’PTIC = 8 courses/ 4 implemented
NCB = 2 courses/2 implemented

## Slide 5: Transitioning face-to-face to online courses
All CoEs except DBI delivered online courses in the 2nd semester.
Train-the-Trainer course on designing and delivering e-learning (online) courses delivered for all ITU Africa CoEs
50 participants
39 completed the final Quiz and successfully completed the course and should receive an ITU Certificate